toggle.solutions

Scope of Work

for [CLIENT LEGAL NAME]

What Toggle will do for you, and by when.

Version 1.0 · 29 September 2026

| What you bought | We start | Your first key date |
| --- | --- | --- |
| Performance Marketing, Search Engine Optimization, Answer Engine Optimization, Generative Engine Optimization, Web Development, Creative Production, Social Media Management | 6 October 2026 | 13 October 2026 |

Prepared by [YOUR NAME], Toggle Solutions

hello@toggle.solutions · toggle.solutions

Delete this page before you send the document.

Everything the generator assumed, and everything it could not work out. Check each line, fix the source, and rebuild.

How the dates were worked out. Dates are counted from the start date, 6 October 2026. A date landing on a Saturday or Sunday moves to the following Monday.

Open items

Performance Marketing: [N] left in 'Plan the campaign structure and the audiences' (amount)

Performance Marketing: [N] left in 'Write the ad copy and brief the creative we need' (amount)

Performance Marketing: [N] left in 'Build and launch the first campaigns' (amount)

Performance Marketing: [N] left in 'Test new audiences, placements or bidding' (amount)

Search Engine Optimization: [N] left in 'Crawl your site and run the technical audit' (amount)

Search Engine Optimization: [N] left in 'Research the keywords worth ranking for' (amount)

Search Engine Optimization: [N] left in 'Apply the technical fixes' (amount)

Search Engine Optimization: [N] left in 'Rewrite page titles and meta descriptions' (amount)

Search Engine Optimization: [N] left in 'Improve the content on your existing pages' (amount)

Answer Engine Optimization: [N] left in 'Find the questions your customers ask before they buy' (amount)

Answer Engine Optimization: [N] left in 'Check which answers Google shows today, and who owns them' (amount)

Answer Engine Optimization: [N] left in 'Rewrite pages so the answer sits in the first paragraph' (amount)

Answer Engine Optimization: [N] left in 'Build or extend your FAQ pages' (amount)

Generative Engine Optimization: [N] left in 'Agree the prompts we will test, written the way your customers ask' (amount)

Generative Engine Optimization: [N] left in 'Run the first test across ChatGPT, Perplexity, Google AI Overviews and Claude' (amount)

Generative Engine Optimization: [N] left in 'Shape your pages so a model can quote them' (amount)

Generative Engine Optimization: [N] left in 'Rerun the prompt test and report what changed' (amount)

Web Development: [N] left in 'Agree the page list and what each page has to do' (amount)

Web Development: [N] left in 'Design the pages' (amount)

Web Development: [N] left in 'Build the pages' (amount)

Web Development: [N] left in 'Set up the forms and where their submissions go' (amount)

Web Development: [N] left in 'Test the site on phone, tablet and desktop' (amount)

Creative Production: [N] left in 'Present the first concepts' (amount)

Creative Production: [N] left in 'Produce the static assets' (amount)

Creative Production: [N] left in 'Edit the short videos' (amount)

Social Media Management: [N] left in 'Agree the content pillars and what each platform is for' (amount)

Social Media Management: [N] left in 'Deliver your first content calendar' (amount)

Social Media Management: [N] left in 'Deliver the calendar for the coming month' (amount)

Social Media Management: [N] left in 'Deliver the calendar for the coming month' (when)

Social Media Management: [N] left in 'Schedule and publish the posts' (amount)

Social Media Management: [N] left in 'Reply to comments and direct messages' (amount)

Social Media Management: [N] left in 'Your offers, promotions and product news, at least [N] working days before you want them posted'

Every [N] above is a number Toggle has not standardized. Set it in the JSON under "amounts", or fix the brain service file if the number is the same for every client.

Before you send

Check the key dates against the timeline in the proposal you sent them.

Check the service list against the quotation, line by line.

Confirm the names, titles and emails in section 2 are current.

Delete this page.

Notes from the draft

This is the reference copy built from example-input.json. It is not a client document.

Copy this file, fill the bracketed fields, delete the services the client did not buy, then rebuild.

1. How to read this document.

This document sets out the work Toggle will do for [CLIENT], how much of it, and when each piece is due. It follows the proposal and the quotation you have already seen, and turns them into dates both of us can hold each other to.

Section 3 lists your key dates in one place. Section 5 breaks the work down by service, and each service names what is not included. Read those two sections and you have the whole agreement.

This document does not carry any prices. Quotation [QUOTATION NUMBER], dated [DATE THE QUOTE WAS SENT], is where the fees live. If the two documents ever disagree on what you are buying, the quotation decides.

If you expected something that is not written here, tell your account lead before you sign. We would rather fix it now than argue about it in month three.

2. What you bought.

| Services | Performance Marketing, Search Engine Optimization, Answer Engine Optimization, Generative Engine Optimization, Web Development, Creative Production, Social Media Management |
| --- | --- |
| Start date | 6 October 2026 |
| Term | 6 months from the start date |
| Review date | [DATE] |
| Quotation | [QUOTATION NUMBER], dated [DATE THE QUOTE WAS SENT] |
| Your account lead at Toggle | [YOUR NAME] |
| Your main contact | [NAME, TITLE] |

3. Your key dates.

Every date we have committed to, in order. Recurring work sits in section 5.

| Date | What is due | Service |
| --- | --- | --- |
| 13 October 2026 | Set up conversion tracking | Performance Marketing |
| 13 October 2026 | Agree the page list and what each page has to do | Web Development |
| 13 October 2026 | Write the creative brief | Creative Production |
| 13 October 2026 | Agree the content pillars and what each platform is for | Social Media Management |
| 20 October 2026 | Build and launch the first campaigns | Performance Marketing |
| 20 October 2026 | Crawl your site and run the technical audit | Search Engine Optimization |
| 20 October 2026 | Check which answers Google shows today, and who owns them | Answer Engine Optimization |
| 20 October 2026 | Run the first test across ChatGPT, Perplexity, Google AI Overviews and Claude | Generative Engine Optimization |
| 20 October 2026 | Present the first concepts | Creative Production |
| 20 October 2026 | Deliver your first content calendar | Social Media Management |
| 27 October 2026 | Give you the fix list, ordered by what moves rankings first | Search Engine Optimization |
| 27 October 2026 | Add structured data to your pages | Answer Engine Optimization |
| 27 October 2026 | Give you the baseline: where you appear, where you do not, and what is said about you | Generative Engine Optimization |
| 27 October 2026 | Design the pages | Web Development |
| 27 October 2026 | First static assets delivered | Creative Production |
| 27 October 2026 | First videos delivered | Creative Production |
| 27 October 2026 | First posts published | Social Media Management |
| 3 November 2026 | First round of technical fixes applied | Search Engine Optimization |
| 3 November 2026 | First pages rewritten as answers | Answer Engine Optimization |
| 10 November 2026 | Your first performance report | Performance Marketing |
| 17 November 2026 | Your first SEO report | Search Engine Optimization |
| 17 November 2026 | Your first AEO report | Answer Engine Optimization |
| 17 November 2026 | Your first GEO visibility report | Generative Engine Optimization |
| 17 November 2026 | Build the pages | Web Development |
| 17 November 2026 | Your first social report | Social Media Management |
| 1 December 2026 | Launch the site | Web Development |

4. What we need from you, and by when.

Every date in section 3 assumes we get these on time.

| What we need | When we need it |
| --- | --- |
| Admin access to every ad account, business manager and analytics property | By 6 October 2026 |
| A payment method loaded on each ad platform | By 6 October 2026 |
| Your offer, your pricing, and the questions your sales team hears most | By 6 October 2026 |
| A developer, or CMS access, so we can place the tracking code | By 6 October 2026 |
| Approval of new ads within three working days of us sending them | Ongoing |
| Your sales or enrollment numbers, so we can tie ad results to revenue | Every month |
| Access to Google Search Console and Google Analytics | By 6 October 2026 |
| CMS admin access, or a developer who can apply our fixes | By 6 October 2026 |
| The products, services and locations you want to be found for | By 6 October 2026 |
| Approval of page changes within five working days | Ongoing |
| Answers from the people in your business who know the subject | By 13 October 2026 |
| CMS access, or a developer who can add the structured data | By 6 October 2026 |
| A short, approved description of what your business does and who it serves | By 13 October 2026 |
| Permission to claim your listings on directories and review sites | By 13 October 2026 |
| The claims you are willing to stand behind in public | By 13 October 2026 |
| Your logo files, fonts, brand colors and any brand guidelines | By 6 October 2026 |
| Hosting, domain and DNS access | By 13 October 2026 |
| All page copy and images | By 20 October 2026 |
| One person who can approve designs on behalf of your business | By 6 October 2026 |
| Feedback on each design round within five working days | Ongoing |
| Your logo files, fonts and brand guidelines | By 6 October 2026 |
| Product photos, footage, or samples we can shoot ourselves | By 13 October 2026 |
| Approval of the creative brief before we start on concepts | By 13 October 2026 |
| Feedback collected into one list per round, sent by one person | Ongoing |
| Admin access to every platform we manage | By 6 October 2026 |
| One person we can ask when a comment needs a real answer from your business | By 6 October 2026 |
| Your offers, promotions and product news, at least [N] working days before you want them posted | Ongoing |
| Approval of the content calendar within three working days | Ongoing |

If something arrives late. If we wait longer than three working days for an approval, or a file arrives late, the dates that depend on it move by the same number of days. We will tell you the new date in writing when it happens.

5. What we will do.

One section per service you bought. Each one lists the work, the amount, and when it happens, then what is not included.

Performance Marketing

Running your ads on the platforms in your quotation, and improving them every week.

| What we will do | How much | When |
| --- | --- | --- |
| Confirm access to your accounts and check what is already tracking | Every ad platform and analytics property in your quotation | By 6 October 2026 |
| Set up conversion tracking | Meta Pixel, GA4 and the Google Ads tag on the pages that matter | By 13 October 2026 |
| Plan the campaign structure and the audiences | [N] campaigns across [N] platforms | By 13 October 2026 |
| Write the ad copy and brief the creative we need | [N] ad variations per campaign | By 20 October 2026 |
| Build and launch the first campaigns | [N] campaigns, [N] ad sets | By 20 October 2026 |
| Review and improve the campaigns | Budget, audience, bid and placement changes | Every week |
| Check your budget pacing so the month lands where you planned | All live campaigns | Every week |
| Test new audiences, placements or bidding | [N] tests a month | Every month |
| Send your performance report | 1 report covering spend, results and cost per result | Every month, by the 5th working day |
| Run your review call | 60 minutes | Every month |

Not in scope

The ad budget itself. You pay Meta, Google and the other platforms directly.

Video and photo shoots. We quote production separately.

Landing page design and build. We quote that separately.

Changes to your website beyond the tracking code.

Calling, emailing or following up the leads the ads bring in.

Setting up or managing your CRM.

Any platform that is not named in your quotation.

Product feed and catalog management for online stores, unless your quotation lists it.

What we need from you

Admin access to every ad account, business manager and analytics property, by 6 October 2026.

A payment method loaded on each ad platform, by 6 October 2026.

Your offer, your pricing, and the questions your sales team hears most, by 6 October 2026.

A developer, or CMS access, so we can place the tracking code, by 6 October 2026.

Approval of new ads within three working days of us sending them, ongoing.

Your sales or enrollment numbers, so we can tie ad results to revenue, every month.

Search Engine Optimization

Making your existing pages rank for the searches your customers already run.

| What we will do | How much | When |
| --- | --- | --- |
| Crawl your site and run the technical audit | Up to [N] pages | By 20 October 2026 |
| Research the keywords worth ranking for | [N] priority keywords | By 20 October 2026 |
| Give you the fix list, ordered by what moves rankings first | 1 document | By 27 October 2026 |
| Apply the technical fixes | Up to [N] fixes a month | Every month |
| Rewrite page titles and meta descriptions | [N] pages a month | Every month |
| Improve the content on your existing pages | [N] pages a month | Every month |
| Link related pages to each other | Across the pages we work on | Every month |
| Watch Search Console for errors and ranking drops | Every indexed page | Every week |
| Send your SEO report | 1 report covering rankings, traffic and the work done | Every month, by the 5th working day |

Not in scope

Writing new blog articles or landing page copy. We quote content separately.

Buying backlinks or paying for links. We do not do it, and it puts your site at risk of a Google penalty.

Redesigning or rebuilding your website.

Translating pages into another language.

Developer work beyond what your CMS lets us change.

Google Ads and any other paid search work.

A guaranteed position for any keyword. Google decides rankings, and no agency can promise one.

What we need from you

Access to Google Search Console and Google Analytics, by 6 October 2026.

CMS admin access, or a developer who can apply our fixes, by 6 October 2026.

The products, services and locations you want to be found for, by 6 October 2026.

Approval of page changes within five working days, ongoing.

Answer Engine Optimization

Getting your answers into the box at the top of Google, and into People Also Ask.

| What we will do | How much | When |
| --- | --- | --- |
| Find the questions your customers ask before they buy | [N] questions | By 20 October 2026 |
| Check which answers Google shows today, and who owns them | The [N] questions above | By 20 October 2026 |
| Add structured data to your pages | FAQ, HowTo, Product or LocalBusiness markup, as your pages need | By 27 October 2026 |
| Rewrite pages so the answer sits in the first paragraph | [N] pages a month | Every month |
| Build or extend your FAQ pages | [N] questions a month | Every month |
| Track which questions you now appear for | 1 report | Every month, by the 5th working day |

Not in scope

A guaranteed answer box or People Also Ask placement. Google chooses what to show and can change it any week.

Writing long-form articles. We quote content separately.

Building new pages or page templates.

The technical SEO work listed under Search Engine Optimization, unless your quotation lists both services.

Video production for video answers.

What we need from you

Answers from the people in your business who know the subject, by 13 October 2026.

CMS access, or a developer who can add the structured data, by 6 October 2026.

Approval of page changes within five working days, ongoing.

Generative Engine Optimization

Getting your business named when someone asks an AI assistant for a recommendation.

| What we will do | How much | When |
| --- | --- | --- |
| Agree the prompts we will test, written the way your customers ask | [N] prompts | By 20 October 2026 |
| Run the first test across ChatGPT, Perplexity, Google AI Overviews and Claude | [N] prompts on 4 engines | By 20 October 2026 |
| Give you the baseline: where you appear, where you do not, and what is said about you | 1 document | By 27 October 2026 |
| Correct your company facts wherever the models read them | Your site, Google Business Profile, directories and review sites | By 3 November 2026 |
| Shape your pages so a model can quote them | [N] pages a month | Every month |
| Rerun the prompt test and report what changed | [N] prompts | Every month, by the 5th working day |

Not in scope

A guaranteed mention. The models decide what they say, and their answers change without notice.

Paying an AI company for placement. No such product exists on these engines today.

Replying to or managing your reviews.

Removing a negative mention from a model's answer.

Creating or editing a Wikipedia page. Wikipedia does not allow paid editing on a client's behalf.

What we need from you

A short, approved description of what your business does and who it serves, by 13 October 2026.

Permission to claim your listings on directories and review sites, by 13 October 2026.

The claims you are willing to stand behind in public, by 13 October 2026.

Web Development

Designing, building and launching the pages listed in your quotation.

| What we will do | How much | When |
| --- | --- | --- |
| Agree the page list and what each page has to do | [N] pages | By 13 October 2026 |
| Design the pages | [N] page designs, 2 rounds of changes | By 27 October 2026 |
| Build the pages | [N] pages, working on phone, tablet and desktop | By 17 November 2026 |
| Set up the forms and where their submissions go | [N] forms | By 17 November 2026 |
| Install analytics and conversion tracking | GA4 and the tags your ads need | By 24 November 2026 |
| Test the site on phone, tablet and desktop | The [N] pages above | By 24 November 2026 |
| Launch the site | 1 launch | By 1 December 2026 |
| Fix anything we built that breaks | Bug fixes only | 30 days from launch |

Not in scope

Writing the copy for the pages. We quote copywriting separately.

Photography, video and illustration.

Hosting, domain and SSL fees. You pay those directly to the provider.

Paid plugins, themes and third-party licenses. You pay those directly.

Maintenance, updates and new pages once the 30 day bug fix window closes.

Any page beyond the number in your quotation.

Online store, payment or booking functions, unless your quotation lists them.

Moving old blog posts or products across from an existing site, unless your quotation lists it.

Mobile app development.

What we need from you

Your logo files, fonts, brand colors and any brand guidelines, by 6 October 2026.

Hosting, domain and DNS access, by 13 October 2026.

All page copy and images, by 20 October 2026.

One person who can approve designs on behalf of your business, by 6 October 2026.

Feedback on each design round within five working days, ongoing.

Creative Production

The brief, the concepts, and the finished assets for the campaigns in your quotation.

| What we will do | How much | When |
| --- | --- | --- |
| Write the creative brief | 1 brief per campaign | By 13 October 2026 |
| Present the first concepts | [N] concepts | By 20 October 2026 |
| Produce the static assets | [N] assets a month, in the sizes each platform needs | Every month |
| Edit the short videos | [N] videos a month, up to [N] seconds each | Every month |
| Write the copy that runs with each asset | 1 set of copy per asset | Every month |
| Resize approved assets for every placement in your media plan | All placements in the plan | Every month |
| Make the changes you ask for | 2 rounds per asset | Every month |

Not in scope

Shoots with a crew, studio, location or talent. We quote production separately.

Talent, model and voiceover fees, and the licenses to keep using their footage.

Stock photo, video and music licenses.

Logo design, brand identity and brand guidelines.

Print, packaging and out of home artwork.

3D, full animation, and motion work beyond simple text and logo movement.

A third round of changes on an asset. We quote that as new work.

What we need from you

Your logo files, fonts and brand guidelines, by 6 October 2026.

Product photos, footage, or samples we can shoot ourselves, by 13 October 2026.

Approval of the creative brief before we start on concepts, by 13 October 2026.

Feedback collected into one list per round, sent by one person, ongoing.

Social Media Management

The calendar, the posts, the captions and the replies on your organic accounts.

| What we will do | How much | When |
| --- | --- | --- |
| Agree the content pillars and what each platform is for | [N] platforms | By 13 October 2026 |
| Deliver your first content calendar | 1 calendar covering [N] posts | By 20 October 2026 |
| Deliver the calendar for the coming month | 1 calendar covering [N] posts | Every month, [N] working days before the month starts |
| Write the captions and hashtags | 1 set per post | Every month |
| Schedule and publish the posts | [N] posts a month on each platform | Every month |
| Reply to comments and direct messages | Within [N] hours, Monday to Friday | Every working day |
| Send your social report | 1 report covering reach, engagement and follower growth | Every month, by the 5th working day |

Not in scope

Paid social ads and the budget behind them. That work sits under Performance Marketing.

Finding, briefing and paying influencers or creators.

Handling complaints, refunds and support questions beyond a first holding reply.

Crisis communications and public statements.

Filming at your events, stores or premises.

Any platform not named in your quotation.

Posts in a language not named in your quotation.

Replies outside Monday to Friday, 9am to 6pm.

What we need from you

Admin access to every platform we manage, by 6 October 2026.

One person we can ask when a comment needs a real answer from your business, by 6 October 2026.

Your offers, promotions and product news, at least [N] working days before you want them posted, ongoing.

Approval of the content calendar within three working days, ongoing.

6. How we work together.

| Your account lead | [YOUR NAME] |
| --- | --- |
| Review call | 60 minutes, once a month |
| Written update | Once a week, by email |
| Reports | By the 5th working day of each month |
| We reply within | One working day, on email |
| We need your approval within | three working days |
| Working hours | Monday to Friday, 9am to 6pm, Malaysia time |
| Public holidays | Malaysian public holidays. We tell you in advance when one affects a date. |

Who to contact

| For | Contact | Email |
| --- | --- | --- |
| Anything about the work, and anything urgent | [NAME], account lead | [EMAIL] |
| Invoices and payment | [NAME] | hello@toggle.solutions |
| Adding work that is not in this document | [NAME], account lead | [EMAIL] |

7. What is not included, and how to add it.

If you want something that is not written in this document, tell your account lead. We will send you a short quote with the cost and the date it would be ready. Work starts once you approve that quote in writing. Nothing outside this document is chargeable to you unless you approved it first, and nothing outside it is owed to you unless we agreed it first.

What can move the dates

An approval that takes longer than three working days.

Content, images or access that arrive after the date in section 4.

A change to your ad budget, which changes what the budget can produce.

An ad, page or account rejected by Meta, Google or another platform under their policies.

A change to what you sell, or to who you sell it to, after this document is signed.

Where one of these happens, we will tell you which dates move and by how much, in writing, within two working days.

8. Sign off.

Signing below confirms that this document describes the work you are buying, and that anything not written in it is not included.

| For [CLIENT LEGAL NAME] Name __________________________ Title __________________________ Signature __________________________ Date __________________________ [NAME, TITLE] | For Toggle Solutions Name __________________________ Title __________________________ Signature __________________________ Date __________________________ [YOUR NAME] |
| --- | --- |

Version history

| Version | Date | What changed | Approved by |
| --- | --- | --- | --- |
| 1.0 | 29 September 2026 | First issue | [YOUR NAME] |